# Proposal: Trade Transaction Management System Implementation

## Objective

To implement an integrated Zoho Books and Zoho Inventory system for managing end-to-end trade transactions. The solution will streamline contracts, shipments, costing, and financial processes while ensuring accurate tracking, reporting, and control.

## Milestone 1: System Setup & Configuration (Zoho Books – Singapore Edition)

- Organization setup (base currency SGD, fiscal year, reporting structure)

- Configure Singapore GST setup (input/output tax, zero-rated, exempt) as per IRAS

- Enable multi-currency transactions and exchange rate handling

- User creation with roles (Ops, Manager, Finance)

- Role-based access control and approval hierarchy setup

- Chart of Accounts setup (Sales, Purchase, LDC, FX Gain/Loss, Expenses)

- Setup bank accounts and reconciliation processes

- Configure document numbering (Invoices, Bills, Credit Notes)

- Enable audit trail and compliance controls

- Setup financial reports (P&L, Balance Sheet, GST reports)

## Milestone 2: Transaction Framework (TS#) Setup

- Create custom field for Transaction Slip Number (TS#) across modules

- Define TS# structure (format: initials + date + sequence) with manual/auto logic

- Configure TS# as a mandatory field for all trade transactions

- Map TS# across Sales Orders, Purchase Orders, Invoices, and Bills

- Ensure TS# flows automatically from upstream to downstream documents

- Create validation rules to prevent duplicate or missing TS#

- Implement logic to maintain one TS# per trade deal lifecycle

- Add TS# as a key reference in all document templates and reports

- Configure search and filtering based on TS# for easy tracking

- Enable reporting and traceability of all transactions at TS# level

## Milestone 3: Contract Management Setup (Custom)

- Configure Sales Orders to function as the Sales Contract module

- Configure Purchase Orders to function as the Purchase Contract module

- Design and implement contract structure aligned with TS# linkage

- Create custom fields for:

  - Product hierarchy (Category, Sub-category, Grade)

  - Incoterms, POL (Port of Loading), POD (Port of Discharge), Destination

  - Payment terms, shipment period, packing details

- Configure standardized contract templates for both sales and purchase sides

- Implement supplier-side mirroring of sales contract (auto-copy key fields to purchase contract) (Custom Logic)

- Define and configure contract numbering series for Sales and Purchase Contracts

- Ensure mandatory field validation for all commercial and logistics details

- Enable linking of contracts with TS# for full traceability

- Configure workflows for contract creation, review, and approval by Manager

- Implement checks to ensure quantity, pricing, and terms consistency between contracts

- Enable document attachments in the module

## Milestone 4: Custom Module Configurations

- Design required custom structures (TS#, contract linkage, LDC tracking, shipment references)

- Create custom fields across modules (Sales Orders, Purchase Orders, Invoices, Bills)

- Configure fields for TS#, contract references, product hierarchy, and logistics details

- Setup LDC components fields (Freight, Insurance, Commission, others)

- Implement workflows for TS# flow, contract mirroring, and status tracking

- Configure validation rules for mandatory fields and data consistency

- Setup approval workflows for contracts and key transactions

- Enable auto-population of data across linked documents

- Configure custom statuses and lifecycle tracking for deals

- Setup notifications and basic reporting visibility for all custom fields

## Milestone 5: Reporting & Dashboards Setup

- Design overall reporting structure aligned with trade lifecycle and TS# tracking

- Create TS#-wise profitability reports (revenue, cost, margin)

- Configure LDC and landed cost reports (budgeted vs actual)

- Setup variance reports for LDC tracking and analysis

- Build AR & AP ageing reports with contract and TS# references

- Configure sales and purchase analysis reports (category, sub-category level)

- Setup multi-currency and FX gain/loss reporting

- Create standard financial reports (P&L, Balance Sheet) with trade-level insights

- Build custom dashboards for Ops and Finance teams

- Enable filters, drill-downs, and export options for all reports

## Milestone 6: Standard Inventory Setup (Zoho Inventory)

- Organization setup for inventory (warehouses, locations, base preferences, document settings)

- Create and configure item master (products, categories, units of measure, SKU/barcode structure)

- Setup inventory and accounting linkage (inventory asset, COGS, stock adjustment accounts)

- Configure warehouses and multi-location stock tracking

- Enable batch/serial number tracking and expiry tracking (if applicable)

- Setup price lists, item pricing, and currency handling

- Configure purchase and sales workflows (PO → GRN/Receive → Sales Order → Delivery)

- Enable stock tracking, reorder levels, and low-stock alerts

- Setup inventory preferences (negative stock handling, approval settings, packing/shipping options)

- Configure basic reports (inventory valuation, stock summary, FIFO/average costing, movement reports)

- Setup vendor and customer item mapping (if required)

- Perform end-to-end testing (procurement → stock inward → fulfillment → stock deduction)

## Milestone 7: UAT and Training

- Prepare UAT plan and test scenarios covering end-to-end trade lifecycle (TS# to reporting)

- Create sample data and test cases for contracts, shipments, LDC, and finance flows

- Execute UAT with key users (Ops, Manager, Finance)

- Validate custom workflows, validations, and reports

- Log issues, perform fixes, and retest critical flows

- Obtain user sign-off for all modules and processes

- Conduct role-based training sessions (Ops, Finance, Management)

- Provide hands-on walkthroughs for daily operations and reporting

- Share user guides / SOP mapping aligned with system workflows

- Provide go-live support and post-training assistance

- types (e.g., hoardings, newspaper ads

## Effort & Cost

- Total Estimated Effort:

- Total Project Cost: