## Sheet1
HELIOS TECH LABS
Zoho Creator App for Villas Management
Pre-Sales Evaluation done basis the Information note provided by the customer
Document Information
Document Number |  | Date
6/68/2025 |  | 2025-06-25
Application & Licenses Details
ZOHO Modules Required: |  | Zoho Creator and Zoho Analytics
Data Loading & Integration Details
Previous/ Existing Software(s) Details
Previous/ Existing Software(s) User:
Data Migration Required (If any) in which apps:
Data Migration Duration: (From to till Date)
Data Will Be provided by customer ?
Format of data: (Excel,CSV, etc.)
Integration Requirements (if any)
Training Details
How many people need to be trained ?
Training Location(s): |  |  | Online/Onsite
Customer Category |  |  | A |  | B
BUSINESS DESCRIPTION
Project Timeline: 40 days
Internal Evaluation: Time Required in Followings (Man Days)
Milestone Name
Milestone 1: Guest Line PMS API Integration and Modules Setup
● API Integration Setup ● Create scheduled/instant API connections to fetch real-time or near real-time data for each villa: daily revenue, occupancy, and future bookings. ● Set up data parsing logic and store it in structured forms (Revenue, Bookings, Occupancy, etc.). ● Data Modeling and Form Design ● Create forms to store: ● Villa Master (owner info, villa ID) ● Daily Revenue ● Occupancy Data ● Booking Data ● Commission/Revenue Sharing structure ● Establish relationships between forms
Milestone 2: Workflows Implementation and Portal Users Access
● Design and implement a flexible business logic module that supports per-villa revenue sharing and commission configurations based on owner agreements. ● Allow for both fixed-rate and percentage-based commission structures to be configured for each villa independently. ● Create a dynamic formula field or Deluge-based workflow that calculates the owner’s revenue share automatically when booking revenue is updated via API or manual entry. ● Log each revenue calculation for transparency and audit purposes, allowing admins to trace and validate revenue splits. ● Enable Zoho Creator's Customer Portal functionality to provide secure and isolated access for individual villa owners. ● For each owner, generate unique portal login credentials and map them to their respective villa(s) using the Villa ID as a linking key. ● Configure record-level permissions using conditional filters so owners can only view and interact with records (bookings, revenue, occupancy) related to their own villa(s). ● Ensure portal dashboard pages dynamically adjust based on the logged-in user’s access scope, showing only relevant KPIs and reports. ● Set up a separate admin access panel with a consolidated view of all villas, booking statuses, and financial performance metrics. ● Build high-level dashboards for management including villa-wise comparison charts, overall revenue trend graphs, and booking forecasts. ● Implement override features in the admin panel to update sharing percentages, booking corrections, or flag anomalies. ● Provide access logs and activity reports for administrators to monitor portal usage and owner interactions.
Milestone 3: Reporting and Analytics
● Dashboard and Analytics in Zoho Creator ● Design custom dashboards using Zoho Creator’s Pages and Kanban/Chart widgets. ● Show graphs, summary cards, and tables for: ● Daily/Monthly Revenue ● Occupancy trends ● Future bookings ● Commission summaries ● Dashboards are owner-specific and visible only after login. ● Reports and Filtering ● Create custom reports within Zoho Creator using Reports module: ● Booking report by date range ● Revenue report with filters ● Occupancy report with calendar view ● Allow exports for each report from portal access.
Milestone 4: Testing and Support
● Perform end-to-end testing of API data fetch to ensure accurate syncing of revenue, bookings, and occupancy from the Guest Line PMS. ● Verify that data is correctly parsed and stored in Zoho Creator forms, with accurate mappings to villa and owner records. ● Test access controls by logging in as different portal users and confirming each user sees only their assigned villa data. ● Validate business model logic by comparing calculated owner share and commissions against expected values for multiple scenarios. ● Review dashboard widgets, charts, and KPIs for visual accuracy and functional interactivity across different devices and roles. ● Conduct training sessions for both villa owners and property management to walk through dashboard usage, data interpretation, and portal navigation.
EVALUATER DETAILS
Name of Evaluator | Signature (Digital) | Comments (If any): | Requester | Reviewed by: (Name)
Ankush Thakur |  |  |  | Jasleen Kaur