## Sheet1
HELIOS TECH LABS
Zoho Marketing Automation Setup
Pre-Sales Evaluation done basis the Information note provided by the customer
Document Information
Document Number |  | Date
6/28/2025 |  | 2025-06-12
Application & Licenses Details
ZOHO Modules Required: |  | Zoho Marketing Automation, Campaigns, Forms, CRM and Survey
Data Loading & Integration Details
Previous/ Existing Software(s) Details
Previous/ Existing Software(s) User:
Data Migration Required (If any) in which apps:
Data Migration Duration: (From to till Date)
Data Will Be provided by customer ?
Format of data: (Excel,CSV, etc.)
Integration Requirements (if any)
Training Details
How many people need to be trained ?
Training Location(s): |  |  | Online/Onsite
Customer Category |  |  | A |  | B
BUSINESS DESCRIPTION
Project Timeline: 16 days
Internal Evaluation: Time Required in Followings (Man Days)
Milestone Name
Milestone 1: Marketing Automation Setup
● Set up Zoho Marketing Automation or Zoho Campaigns, including sender configuration and domain authentication ● Import or sync contacts and segment them based on categories like new leads, existing customers, VIPs, and inactive users ● Build automated journeys for lead nurturing, abandoned cart follow-up, feedback requests, and reactivation campaigns ● Create and schedule email campaigns using responsive, branded templates with personalization and A/B testing
Milestone 2: Webform Integration
● Build customized webforms for newsletter signups, lead capture, or product inquiries with necessary fields and source tracking ● Embed webforms on the website using iframe or JavaScript and test on desktop and mobile ● Set automation rules to add form submissions to contact lists, trigger welcome emails, and notify internal teams ● Enable CAPTCHA or spam protection to prevent bot submissions and ensure data quality ● Configure double opt-in confirmation emails to validate user interest and maintain compliance ● Set up thank-you pages or redirect URLs after form submission to guide users to the next step (e.g., resource download, scheduling page)
Milestone 3: Zoho Survey Setup
● Design survey forms for post-purchase feedback, NPS, and event feedback using logic-based questions ● Distribute surveys via email, WhatsApp, or website embedding and schedule automatic follow-ups ● Map survey responses to customer segments and generate reports or dashboards for analysis and action ● Customize survey themes with your brand logo, colors, and fonts to ensure consistent branding ● Use conditional logic and skip patterns to personalize the survey experience based on respondent input ● Set up real-time alerts or notifications for specific responses, such as low satisfaction or negative feedback
Milestone 4: Whatsapp Integration
● Choose a WhatsApp Business API provider like Gupshup or Twilio and integrate with Zoho using API or webhooks ● Register and verify a WhatsApp Business account and number, and complete integration steps ● Create WhatsApp message templates for categories such as lead engagement, order updates, promotions, retention, and reminders ● Get templates approved via the WhatsApp Business API provider dashboard ● Segment contact lists for WhatsApp campaigns based on behavior and customer type, such as new users, repeat buyers, or inactive users ● Configure automated WhatsApp messages using Zoho journey builder or through triggered workflows based on events like form submissions, birthdays, or purchases ● Collect and manage opt-ins using webform checkboxes or SMS confirmation to ensure compliance ● Track delivery, read, click-through, and reply rates for each campaign and export reports for review
Milestone 5: Micros POS Integration
● Define integration goals between Micros POS and Zoho CRM ● Identify data fields to sync such as customer info, purchase history, and loyalty points ● Gather API or database access credentials from Micros POS ● Map Micros POS fields to Zoho CRM modules and custom fields ● Customize Zoho CRM modules to accommodate POS data (e.g., Purchase History, Loyalty Details) ● Build or configure middleware or API scripts to connect Micros POS and Zoho CRM ● Set rules for syncing: create/update logic, sync frequency, and data direction ● Test data flow for customer creation, updates, and transaction syncing ● Implement error logging, retries, and sync failure alerts ● Go live with monitoring and user training on POS-linked CRM data usage
Milestone 6: Testing
● Test email and WhatsApp templates internally for format, links, and personalization accuracy ● Simulate webform and survey submissions to confirm automation and list segmentation are working correctly ● Test different customer journeys to ensure correct message delivery timing and logic ● Verify tracking and analytics for email and WhatsApp campaigns ● Conduct internal user training on how to run campaigns, manage contacts, and interpret results ● Schedule live campaigns with phased rollout and real-time monitoring
EVALUATER DETAILS
Name of Evaluator | Signature (Digital) | Comments (If any): | Requester | Reviewed by: (Name)
Ankush Thakur |  |  |  | Jasleen Kaur